## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Propuesta de tesis | 311 days | July 25, 2022 8:00 AM | May 31, 2023 5:00 PM |  | 1
2 | Yes | Manually Scheduled | Revisión de la literatura | 70 days | July 25, 2022 8:00 AM | October 2, 2022 5:00 PM |  | 2
3 | Yes | Manually Scheduled | Escritura de la propuesta | 210 days | October 3, 2022 8:00 AM | April 30, 2023 5:00 PM |  | 2
4 | Yes | Manually Scheduled | Preparación de presentación | 22 days | May 1, 2023 8:00 AM | May 22, 2023 5:00 PM |  | 2
5 | Yes | Manually Scheduled | Presentación | 1 day | May 31, 2023 8:00 AM | May 31, 2023 5:00 PM |  | 2
6 | Yes | Auto Scheduled | Desarrollo de la investigación | 114 days | July 24, 2023 8:00 AM | November 14, 2023 5:00 PM |  | 1
7 | Yes | Manually Scheduled | Configuración Inicial del proyecto | 2 days | July 24, 2023 8:00 AM | July 25, 2023 5:00 PM |  | 2
8 | Yes | Manually Scheduled | Importación de librería de lattices | 0.5 days | July 24, 2023 8:00 AM | July 24, 2023 12:00 PM |  | 3
9 | Yes | Manually Scheduled | Importación de librería de estenografía | 0.5 days | July 24, 2023 8:00 AM | July 24, 2023 12:00 PM |  | 3
10 | Yes | Manually Scheduled | Creación de makefiles | 1 day | July 25, 2023 8:00 AM | July 25, 2023 5:00 PM |  | 3
11 | Yes | Manually Scheduled | Marco de pruebas | 3 days | July 26, 2023 8:00 AM | July 28, 2023 5:00 PM |  | 2
12 | Yes | Manually Scheduled | Diseño | 1 day | July 26, 2023 8:00 AM | July 26, 2023 5:00 PM |  | 3
13 | Yes | Manually Scheduled | Implementación | 2 days | July 27, 2023 8:00 AM | July 28, 2023 5:00 PM |  | 3
14 | Yes | Manually Scheduled | Modelo de seguridad multinivel | 9 days | July 29, 2023 8:00 AM | August 6, 2023 5:00 PM |  | 2
15 | Yes | Auto Scheduled | Diseño e implementación | 7 days | July 29, 2023 8:00 AM | August 4, 2023 5:00 PM |  | 3
16 | Yes | Manually Scheduled | Configuración | 1 day | July 29, 2023 8:00 AM | July 29, 2023 5:00 PM |  | 4
17 | Yes | Auto Scheduled | Generación de llaves | 0.5 days | July 29, 2023 8:00 AM | July 29, 2023 12:00 PM |  | 5
18 | Yes | Manually Scheduled | Manejo de datos de entrada | 0.5 days | July 29, 2023 8:00 AM | July 29, 2023 12:00 PM |  | 5
19 | Yes | Manually Scheduled | Emisor | 2 days | July 30, 2023 8:00 AM | July 31, 2023 5:00 PM |  | 4
20 | Yes | Manually Scheduled | Encriptación de mensajes | 0.5 days | July 30, 2023 8:00 AM | July 30, 2023 12:00 PM |  | 5
21 | Yes | Manually Scheduled | Empotrado de imágenes | 1.5 days | July 30, 2023 8:00 AM | July 31, 2023 12:00 PM |  | 5
22 | Yes | Manually Scheduled | Paso de mensajes | 1 day | August 1, 2023 8:00 AM | August 1, 2023 5:00 PM |  | 4
23 | Yes | Manually Scheduled | Receptor | 2 days | August 2, 2023 8:00 AM | August 3, 2023 5:00 PM |  | 4
24 | Yes | Manually Scheduled | Desempotrado de imágenes | 1.5 days | August 2, 2023 8:00 AM | August 3, 2023 12:00 PM |  | 5
25 | Yes | Manually Scheduled | Desencriptación de mensajes | 0.5 days | August 3, 2023 8:00 AM | August 3, 2023 12:00 PM |  | 5
26 | Yes | Manually Scheduled | Evaluación de desempeño | 1 day | August 4, 2023 8:00 AM | August 4, 2023 5:00 PM |  | 4
27 | Yes | Manually Scheduled | Forma numérica | 0.5 days | August 4, 2023 8:00 AM | August 4, 2023 12:00 PM |  | 5
28 | Yes | Manually Scheduled | Forma gráfica | 0.5 days | August 4, 2023 8:00 AM | August 4, 2023 12:00 PM |  | 5
29 | Yes | Manually Scheduled | Pruebas unitarias | 2 days | August 5, 2023 8:00 AM | August 6, 2023 5:00 PM |  | 3
30 | Yes | Manually Scheduled | Modelo de seguridad multinivel vectorizado | 44 days | August 7, 2023 8:00 AM | September 19, 2023 5:00 PM |  | 2
31 | Yes | Auto Scheduled | Diseño e implementación | 40 days | August 7, 2023 8:00 AM | September 15, 2023 5:00 PM |  | 3
32 | Yes | Manually Scheduled | Criptografía | 22 days | August 7, 2023 8:00 AM | August 28, 2023 5:00 PM |  | 4
33 | Yes | Manually Scheduled | Diseño | 2 days | August 7, 2023 8:00 AM | August 8, 2023 5:00 PM |  | 5
34 | Yes | Manually Scheduled | Implementación | 8 days | August 9, 2023 8:00 AM | August 16, 2023 5:00 PM |  | 5
35 | Yes | Manually Scheduled | Encriptación | 4 days | August 9, 2023 8:00 AM | August 12, 2023 5:00 PM |  | 6
36 | Yes | Manually Scheduled | Desencriptación | 4 days | August 13, 2023 8:00 AM | August 16, 2023 5:00 PM |  | 6
37 | Yes | Manually Scheduled | Perfilado | 6 days | August 17, 2023 8:00 AM | August 22, 2023 5:00 PM |  | 5
38 | Yes | Manually Scheduled | Encriptación | 3 days | August 17, 2023 8:00 AM | August 19, 2023 5:00 PM |  | 6
39 | Yes | Manually Scheduled | Desencriptación | 3 days | August 20, 2023 8:00 AM | August 22, 2023 5:00 PM |  | 6
40 | Yes | Manually Scheduled | Ajustes | 2 days | August 23, 2023 8:00 AM | August 24, 2023 5:00 PM |  | 5
41 | Yes | Manually Scheduled | Encriptación | 1 day | August 23, 2023 8:00 AM | August 23, 2023 5:00 PM |  | 6
42 | Yes | Manually Scheduled | Desencriptación | 1 day | August 24, 2023 8:00 AM | August 24, 2023 5:00 PM |  | 6
43 | Yes | Manually Scheduled | Estenografía | 22 days | August 25, 2023 8:00 AM | September 15, 2023 5:00 PM |  | 4
44 | Yes | Manually Scheduled | Diseño | 2 days | August 25, 2023 8:00 AM | August 26, 2023 5:00 PM |  | 5
45 | Yes | Manually Scheduled | Implementación | 8 days | August 27, 2023 8:00 AM | September 3, 2023 5:00 PM |  | 5
46 | Yes | Manually Scheduled | Empotrado | 4 days | August 27, 2023 8:00 AM | August 30, 2023 5:00 PM |  | 6
47 | Yes | Manually Scheduled | Desempotrado | 4 days | August 31, 2023 8:00 AM | September 3, 2023 5:00 PM |  | 6
48 | Yes | Manually Scheduled | Perfilado | 6 days | September 4, 2023 8:00 AM | September 9, 2023 5:00 PM |  | 5
49 | Yes | Manually Scheduled | Empotrado | 3 days | September 4, 2023 8:00 AM | September 6, 2023 5:00 PM |  | 6
50 | Yes | Manually Scheduled | Desempotrado | 3 days | September 7, 2023 8:00 AM | September 9, 2023 5:00 PM |  | 6
51 | Yes | Manually Scheduled | Ajustes | 2 days | September 10, 2023 8:00 AM | September 11, 2023 5:00 PM |  | 5
52 | Yes | Manually Scheduled | Empotrado | 1 day | September 10, 2023 8:00 AM | September 10, 2023 5:00 PM |  | 6
53 | Yes | Manually Scheduled | Desempotrado | 1 day | September 11, 2023 8:00 AM | September 11, 2023 5:00 PM |  | 6
54 | Yes | Manually Scheduled | Pruebas unitarias | 8 days | September 12, 2023 8:00 AM | September 19, 2023 5:00 PM |  | 3
55 | Yes | Manually Scheduled | Modelo de seguridad multinivel multihilo | 44 days | September 20, 2023 8:00 AM | November 2, 2023 5:00 PM |  | 2
56 | Yes | Auto Scheduled | Diseño e implementación | 40 days | September 20, 2023 8:00 AM | October 29, 2023 5:00 PM |  | 3
57 | Yes | Manually Scheduled | Criptografía | 22 days | September 20, 2023 8:00 AM | October 11, 2023 5:00 PM |  | 4
58 | Yes | Manually Scheduled | Diseño | 2 days | September 20, 2023 8:00 AM | September 21, 2023 5:00 PM |  | 5
59 | Yes | Manually Scheduled | Implementación | 8 days | September 22, 2023 8:00 AM | September 29, 2023 5:00 PM |  | 5
60 | Yes | Manually Scheduled | Encriptación | 4 days | September 22, 2023 8:00 AM | September 25, 2023 5:00 PM |  | 6
61 | Yes | Manually Scheduled | Desencriptación | 4 days | September 26, 2023 8:00 AM | September 29, 2023 5:00 PM |  | 6
62 | Yes | Manually Scheduled | Perfilado | 6 days | September 30, 2023 8:00 AM | October 5, 2023 5:00 PM |  | 5
63 | Yes | Manually Scheduled | Encriptación | 3 days | September 30, 2023 8:00 AM | October 2, 2023 5:00 PM |  | 6
64 | Yes | Manually Scheduled | Desencriptación | 3 days | October 3, 2023 8:00 AM | October 5, 2023 5:00 PM |  | 6
65 | Yes | Manually Scheduled | Ajustes | 2 days | October 6, 2023 8:00 AM | October 7, 2023 5:00 PM |  | 5
66 | Yes | Manually Scheduled | Encriptación | 1 day | October 6, 2023 8:00 AM | October 6, 2023 5:00 PM |  | 6
67 | Yes | Manually Scheduled | Desencriptación | 1 day | October 7, 2023 8:00 AM | October 7, 2023 5:00 PM |  | 6
68 | Yes | Manually Scheduled | Estenografía | 22 days | October 8, 2023 8:00 AM | October 29, 2023 5:00 PM |  | 4
69 | Yes | Manually Scheduled | Diseño | 2 days | October 8, 2023 8:00 AM | October 9, 2023 5:00 PM |  | 5
70 | Yes | Manually Scheduled | Implementación | 8 days | October 10, 2023 8:00 AM | October 17, 2023 5:00 PM |  | 5
71 | Yes | Manually Scheduled | Empotrado | 4 days | October 10, 2023 8:00 AM | October 13, 2023 5:00 PM |  | 6
72 | Yes | Manually Scheduled | Desempotrado | 4 days | October 14, 2023 8:00 AM | October 17, 2023 5:00 PM |  | 6
73 | Yes | Manually Scheduled | Perfilado | 6 days | October 18, 2023 8:00 AM | October 23, 2023 5:00 PM |  | 5
74 | Yes | Manually Scheduled | Empotrado | 3 days | October 18, 2023 8:00 AM | October 20, 2023 5:00 PM |  | 6
75 | Yes | Manually Scheduled | Desempotrado | 3 days | October 21, 2023 8:00 AM | October 23, 2023 5:00 PM |  | 6
76 | Yes | Manually Scheduled | Ajustes | 2 days | October 24, 2023 8:00 AM | October 25, 2023 5:00 PM |  | 5
77 | Yes | Manually Scheduled | Empotrado | 1 day | October 24, 2023 8:00 AM | October 24, 2023 5:00 PM |  | 6
78 | Yes | Manually Scheduled | Desempotrado | 1 day | October 25, 2023 8:00 AM | October 25, 2023 5:00 PM |  | 6
79 | Yes | Manually Scheduled | Pruebas unitarias | 8 days | October 26, 2023 8:00 AM | November 2, 2023 5:00 PM |  | 3
80 | Yes | Manually Scheduled | Modelo de seguridad multinivel multihilo y vectorizado | 12 days | November 3, 2023 8:00 AM | November 14, 2023 5:00 PM |  | 2
81 | Yes | Manually Scheduled | Diseño e implementación | 8 days | November 3, 2023 8:00 AM | November 10, 2023 5:00 PM |  | 3
82 | Yes | Manually Scheduled | Acoplamiento de la solución multihilo | 1 day | November 3, 2023 8:00 AM | November 3, 2023 5:00 PM |  | 4
83 | Yes | Manually Scheduled | Acoplamiento de la vectorización | 1 day | November 4, 2023 8:00 AM | November 4, 2023 5:00 PM |  | 4
84 | Yes | Manually Scheduled | Perfilado | 4 days | November 5, 2023 8:00 AM | November 8, 2023 5:00 PM |  | 4
85 | Yes | Manually Scheduled | Ajustes | 2 days | November 9, 2023 8:00 AM | November 10, 2023 5:00 PM |  | 4
86 | Yes | Manually Scheduled | Pruebas Unitarias | 4 days | November 11, 2023 8:00 AM | November 14, 2023 5:00 PM |  | 3
87 | Yes | Manually Scheduled | Tesis | 119 days | February 5, 2024 8:00 AM | June 2, 2024 5:00 PM |  | 1
88 | Yes | Manually Scheduled | Introducción | 17 days | February 5, 2024 8:00 AM | February 21, 2024 5:00 PM |  | 2
89 | Yes | Manually Scheduled | Marco teórico | 12 days | February 22, 2024 8:00 AM | March 4, 2024 5:00 PM |  | 2
90 | Yes | Manually Scheduled | Diseño | 24 days | March 5, 2024 8:00 AM | March 28, 2024 5:00 PM |  | 2
91 | Yes | Manually Scheduled | Desarrollo | 35 days | March 29, 2024 8:00 AM | May 2, 2024 5:00 PM |  | 2
92 | Yes | Manually Scheduled | Resultados | 17 days | May 3, 2024 8:00 AM | May 19, 2024 5:00 PM |  | 2
93 | Yes | Manually Scheduled | Conclusiones | 14 days | May 20, 2024 8:00 AM | June 2, 2024 5:00 PM |  | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units